## Slide 1: Chapter 8
Cost Estimation and Budgeting

## Slide 2: Chapter 8 Learning Objectives
After completing this chapter, students will be able to:
Understand the various types of common project costs.
Recognize the difference between various forms of project costs.
Apply common forms of cost estimation for project work, including ballpark estimates and definitive estimates.
Understand the advantages of parametric cost estimation and the application of learning curve models in cost estimation.

## Slide 3: Chapter 8 Learning Objectives
After completing this chapter, students will be able to:
Discern the various reasons why project cost estimation is often done poorly.
Apply both top-down and bottom-up budgeting procedures for cost management.
Understand the uses of activity-based budgeting and time-phased budgets for cost estimation and control.
Recognize the appropriateness of applying contingency funds for cost estimation.

## Slide 4: Cost Management
Cost management has been defined to encompass data collection, cost accounting, and cost control.
Cost accounting and cost control serve as the chief mechanisms for identifying and maintaining control over project costs.
Cost estimation processes create a reasonable budget baseline for the project.

## Slide 5: Common Sources of Project Cost
Labor
Materials
Subcontractors
Equipment & facilities
Travel

## Slide 6: Types of Costs
Direct Vs. Indirect
Recurring Vs. Nonrecurring
Fixed Vs. Variable
Normal Vs. Expedited

## Slide 7: Cost Classifications
Direct Labor | X |  | X |  | X |  | X | 
Building Lease |  | X | X |  | X |  | X | 
Expedite | X |  |  | X |  | X |  | X
Material | X |  | X |  |  | X | X | 
Non-recurring
Direct
Indirect
Fixed
Recurring
Variable
Normal
Expedited
Costs
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 8: Cost Estimation
Ballpark (order of magnitude) ±30%
Comparative ±15%
Feasibility ±10%
Definitive ±5%

## Slide 9: Parametric Estimate for Design Costs for Concorde
FIGURE 8.2
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 10: Learning Curves
Each doubling of output results in a reduction in time to perform the last iteration.

## Slide 11: Unit Learning Curve Log-Linear Model
FIGURE 8.4
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 12: Software Project Estimation – Function Points
Function Point Analysis is a system for estimating the size of software projects based on what the software does.
Function points are a standard unit of measure that represents the functional size of a software application.

## Slide 13: Software Project Development Activities as a Function of Size
FIGURE 8.5
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 14: Complexity Weighting Table for Function Point Analysis
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 15: Function Point Calculations for Restaurant Reorder System
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 16: Problems with Cost Estimation
Low initial estimates
Unexpected technical difficulties
Lack of definition
Specification changes
External factors

## Slide 17: Creating a Project Budget
Top-down
Bottom-up
Activity-based costing (ABC)
Project Plan
WBS
Scheduling
Budgeting
The budget is a plan that identifies the resources, goals and schedule that allows a firm to achieve those goals

## Slide 18: Activity-Based Costing
Projects use activities & activities use resources
Assign costs to activities that use resources
Identify cost drivers associated with this activity
Compute a cost rate per cost driver unit or transaction
Multiply the cost driver rate times the volume of cost driver units used by the project

## Slide 19: Sample Project Budget
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall
Table 8.6

## Slide 20: Sample Budget Tracking Planned and Actual Activity Costs
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall
Table 8.7

## Slide 21: Example of a Time-Phased Budget
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall
Table 8.8

## Slide 22: Cumulative Budgeted Cost of the Project
Figure 8.7
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 23: Budget Contingencies
The allocation of extra funds to cover uncertainties and improve the chance of finishing on time.
Contingencies are needed because
Project scope may change
Murphy’s Law is present
Cost estimation must anticipate interaction costs
Normal conditions are rarely encountered

## Slide 24: Summary
Understand the various types of common project costs.
Recognize the difference between various forms of project costs.
Apply common forms of cost estimation for project work, including ballpark estimates and definitive estimates.
Understand the advantages of parametric cost estimation and the application of learning curve models in cost estimation.

## Slide 25: Summary
Discern the various reasons why project cost estimation is often done poorly.
Apply both top-down and bottom-up budgeting procedures for cost management.
Understand the uses of activity-based budgeting and time-phased budgets for cost estimation and control.
Recognize the appropriateness of applying contingency funds for cost estimation.

## Slide 26
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall